PROPERTY AND PLANT TESTING AND COMMISSIONING CLAUSE

- It is hereby noted and agreed that this (Re)Insurance does not cover loss, destruction of or damage to property or plant in the course of:

  - construction or erection;

  - dismantling;

  - revamp;

  - pre-commissioning;

  - commissioning (including start-up);

  - ramp-up to 100% of design capacity;

  - demonstration of satisfactory plant operation at 100% of design capacity;

and any loss resulting from interruption or interference with the business carried on by the (Re)Insured in consequence of 1.1. to 1.7. above.

- Acceptance of property or plant onto this (Re)Insurance is subject to satisfactory completion of the following:

  - Mechanical completion.

  - Pre-commissioning, commissioning including start-up and ramp-up to 100% design capacity.

  - Demonstration of satisfactory plant operation at 100% design capacity having been maintained by the entire plant in a stable and controlled manner for a continuous period and with a minimum duration of 72 hours.

  - Acceptance of the property or plant by the (Re)Insured following formal hand over of care, custody and control, without reservation or waiver of guarantee conditions.

  - Declaration of any remaining deficiencies identified during the construction, pre-commissioning, commissioning, start-up, ramp-up and demonstration of satisfactory plant operation at 100% design capacity that may affect the mechanical integrity, process safety or reliability of the plant, having been made to (Re)Insurers prior to attachment.

- (Re)Insurers request completion of the “Information to support the transfer of Onshore Oil, Gas and Petrochemical Assets from Construction to Operational (Re)Insurance” form as attached, to support this clause.

- Acceptance of property and plant onto this (Re)Insurance is to be agreed by (Re)Insurers as evidenced by an endorsement to this (Re)Insurance.

- It is further noted and agreed that the above provisions do not apply to property and plant that are subject to maintenance activities including turnarounds and / or minor works, as defined in this (Re)Insurance.

Information to support the transfer of

Onshore Oil, Gas and Petrochemical assets

from Construction to Operational (RE)insurance

Purpose

The purpose of the following form is to facilitate the transfer of Onshore Oil, Gas and Petrochemical assets from a construction (Re)Insurance to an operational (Re)Insurance. To facilitate this transfer of assets, it is requested that the (Re)Insured completes this form to the best of their knowledge.

The information provided is intended to:

- support paragraphs 2.1 to 2.5 of the Property and Plant Testing and Commissioning Clause;

- help define items of critical importance to (Re)Insurers for the initial safe operation of an asset following start-up;

- help (Re)Insurers understand the risks to be transferred thus allowing for accurate and detailed underwriting and an informed decision to be made regarding coverage;

- be of mutual benefit to the (Re)Insured, Broker and (Re)Insurers by clarifying expectations for the transfer to operational cover; and

- form the basis for discussion between the (Re)Insured and (Re)Insurers, with identified issues providing an aid to mutual understanding between the parties to prevent these issues from becoming a barrier to any transfer of assets.

This form is not intended to replace any other information which may be provided within the (Re)Insured’s/Broker’s submission.

Process

It is intended that this form will be completed by persons knowledgeable in the specific topic areas. Completion of the form may require coordination between different responsible parties within the (Re)Insureds’ and Brokers’ organisations.

It is expected that the form will be completed for all applicable endorsements transferring assets from construction to operational (Re)Insurance.

The completed form should be submitted to (Re)Insurers before the anticipated operational (Re)Insurance inception date. The intent is that the information contained within this form reflects the status of the asset as close to inception as possible whilst allowing a reasonable time for the information to be reviewed by (Re)Insurers.

| (Re)Insured’s Name |  |
| --- | --- |
| Project Name |  |
| Proposed Date of Inception of Operational Cover |  |
| Date Information Completed |  |

Please provide attachments where necessary to support the following information requests.

|  | Overview |
| --- | --- |
|  | Provide details of the full scope of assets to be transferred. |
|  | Provide details of the start-up plan including a schedule with the order and approximate dates in which units will be/were started up. Include details of any units which will be started up and subsequently idled. |
|  | Provide details of any restrictions on the ability to demonstrate 100% design capacity. |

|  | Mechanical Completion |  |  |  |
| --- | --- | --- | --- | --- |
|  | Was a certificate of Mechanical Completion issued to the Owner? |  |  |  |
|  | YES |  | NO |  |
|  | Provide details of any significant quality related issues with materials or equipment (e.g. major fabrication defects, material non-conformity, large-scale welding non-conformities) which could affect the mechanical integrity of the plant. Provide a summary of what has been done to rectify these faults. |  |  |  |

|  | Pre-commissioning and commissioning including start-up and ramp-up to 100% design capacity |  |  |  |
| --- | --- | --- | --- | --- |
|  | Have there been any insurance claims on the Construction (Re)Insurance? |  |  |  |
|  | YES |  | NO |  |
|  | If yes, provide details below. |  |  |  |
|  | Have there been any significant incidents, not necessarily resulting in an insurance claim, during the project? Examples would include a significant Loss of Primary Containment (LOPC), fire, explosion, machinery breakdown, dropped load or equipment damage. |  |  |  |
|  | YES |  | NO |  |
|  | If yes, provide details below. |  |  |  |
|  | Are there any significant remaining construction works taking place on the plant that could present a risk to the plant when handed over to Operations (e.g. simultaneous construction and operation (SIMOPS))? |  |  |  |
|  | YES |  | NO |  |
|  | If yes, provide details below. |  |  |  |
|  | Provide details of the current status of all Safety Critical Equipment as per the definitions below and the following table. |  |  |  |
|  | - Tested - all such systems have been tested against a predefined performance standard. This should include the full loop from detection device (e.g. sensor) to final element (e.g. isolation valve). In the case of fire protection systems, this should include a full functional test. In the case of mechanical pressure relief devices, this means that the equipment has been tested and certified as per the original design specification. |  |  |  |
|  | - In Service - all such systems are available to the process should a demand be placed upon them i.e. no impairment/override/bypass of individual systems. |  |  |  |
|  | - Deviations/Impairments - record any individual systems which do not meet the Tested and/or In Service criteria as outlined above. Details of any long-term impairments should be provided here. |  |  |  |

| Safety Critical Equipment | 100% Tested (i) |  |  |  | 100% In Service (ii) |  |  |  | Deviations/Impairments (iii) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trip and Alarm Systems for example: - Emergency Shut Down (ESD), Isolation and Depressurisation systems - Reactor kill and dump systems - Safety trips and interlocks including Safety Instrumented Functions - Safety critical alarms - Safety critical analysers - Machinery protection systems (for example overspeed, vibration) - Fired heater protection systems (for example fuel supply low pressure) - Any safety instrumentation as part of a vendor supplied package | YES |  | NO |  | YES |  | NO |  |  |
| Mechanical Relief Devices for example: - Over Pressure Protection Devices - Vacuum Relief Devices - Thermal Relief Devices | YES |  | NO |  | YES |  | NO |  |  |
| Mechanical Interlocks | YES |  | NO |  | YES |  | NO |  |  |
| Emergency Power Supply for example: - Uninterruptible Power Supply (UPS) - Emergency Diesel Generator(s) | YES |  | NO |  | YES |  | NO |  |  |
| Remotely Operable Emergency Isolation Valves (ROIVs) | YES |  | NO |  | YES |  | NO |  |  |
| Fire and Gas Detection systems for example: - Smoke detection in business-critical buildings - Flammable gas detection in open plant and enclosures - Flame and heat detection in open plant and enclosures | YES |  | NO |  | YES |  | NO |  |  |
| Fire Protection systems for example: - Firewater storage, pumps and distribution - Hydrants, monitors and deluge systems - Foam and powder systems - Gaseous extinguishing systems | YES |  | NO |  | YES |  | NO |  |  |

|  | Demonstration of satisfactory plant operation at 100% design capacity, having been maintained by the entire plant in a stable and controlled manner for a continuous period and with a minimum duration of 72 hours |  |  |  |
| --- | --- | --- | --- | --- |
|  | Provide continuous production data from the start of operations to date for the plant and identify the 72-hour period where 100% design capacity was demonstrated for which hourly data should be provided. |  |  |  |
|  | If it is not possible to achieve the 100% design capacity, provide details as to the reasons why and provide continuous production data from the start of operations to date, with hourly data for the period where maximum achieved capacity was demonstrated. |  |  |  |
|  | Are there any major equipment items which have not yet demonstrated 100% design capacity but are to be attached under this endorsement? This is not intended to cover installed spare equipment (e.g. pump A and pump B) but rather major equipment items which have not yet been utilised, for example, due to product grade runs. |  |  |  |
|  | YES |  | NO |  |
|  | If yes, provide details below. |  |  |  |
|  | During the demonstration of plant operation at 100% design capacity were all other process variables within the original process design specification? |  |  |  |
|  | YES |  | NO |  |
|  | If no, provide details below. |  |  |  |
|  | Were any plant performance issues highlighted during ramp-up and operation at 100% design capacity? |  |  |  |
|  | YES |  | NO |  |
|  | If yes, provide details below. |  |  |  |

|  | Acceptance by the (Re)Insured following formal hand over of care, custody and control of the plant without reservation or waiver of guarantee conditions. |  |  |  |
| --- | --- | --- | --- | --- |
|  | Has the project been accepted by the owner following formal handover without reservation or waiver of guarantee conditions? |  |  |  |
|  | YES |  | NO |  |
|  | If no, provide details below. A copy of the formal handover document is requested. |  |  |  |

|  | Provide details of any remaining deficiencies identified during the construction, pre-commissioning, commissioning, start-up, ramp-up and demonstration of satisfactory plant operation at 100% design capacity that may affect the mechanical integrity6.1, process safety6.2 or reliability6.3 of the plant. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mechanical Integrity |  |  |  |  |  |  |  |
|  | Are there any equipment faults, warranty issues, fabrication defects, temporary modifications or punch list items remaining which could potentially affect the mechanical integrity of the plant? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | If yes, provide details below. |  |  |  |  |  |  |  |
|  | Provide a copy of the latest status of any punch list items which could potentially affect the mechanical integrity of the plant. |  |  |  |  |  |  |  |
|  | Process Safety |  |  |  |  |  |  |  |
|  | Was a formal Pre-Start-up Safety Review (PSSR) completed for the project? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | Were the following items considered, confirmed and accepted during the PSSR (or equivalent procedure): |  |  |  |  |  |  |  |
|  | Status of all Process Hazard Analysis (PHA) (e.g. HAZOP) actions? |  |  |  | YES |  | NO |  |
|  | Availability of Start-Up, Shutdown and Emergency Operating Procedures? |  |  |  | YES |  | NO |  |
|  | Delivery of training to Operators and Maintenance technicians? |  |  |  | YES |  | NO |  |
|  | Availability of as-built piping and instrumentation diagrams (P&IDs) to Operational staff? |  |  |  | YES |  | NO |  |
|  | If no to any of the above, provide details below. |  |  |  |  |  |  |  |
|  | Is there a formal and documented Management of Change (MoC) procedure in place for the operational phase covering all permanent, temporary and emergency changes? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | Is there an operational procedure in place to manage and authorise the temporary override/bypass of Safety Instrumented Functions? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | Is there an operational procedure in place to manage and authorise the temporary impairment of fire protection systems and any other Safety Critical Equipment? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | Is the Operations organisation fully staffed in respect of the agreed headcount? Is additional management and technical resource available during start-up? Are overtime hours being monitored and controlled? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | If no to any of the above, provide details below. |  |  |  |  |  |  |  |
|  | Is the Emergency Response Team (ERT) fully staffed, equipped and trained? Is the ERT aware of current plant status and any special procedures necessary? Is free and uninhibited access to the plant possible? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | If no to any of the above, provide details below. |  |  |  |  |  |  |  |
|  | Reliability |  |  |  |  |  |  |  |
|  | Are there any current known recurring process or equipment (mechanical, electrical and instrumentation) issues affecting the reliability of plant operation? |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | If yes, provide details below. |  |  |  |  |  |  |  |
|  | Are major spares available for large unspared long delivery equipment items which could, if they failed, result in a significant business interruption impact (several months plant shutdown)? Examples of these ‘insurance’ spares are compressor or turbine shafts, large electric motors or large transformers. |  |  |  |  |  |  |  |
|  | YES |  | NO |  |  |  |  |  |
|  | If no, provide details below. |  |  |  |  |  |  |  |

LMA5197C
21 July 2025